TaLender – Project Booklet

Authors: Wei Han• Luca Attanasio • Simone Cerino
Process: 4 Sprints × 2 weeks (≈ 2 months)

# 1. Project Overview

| Project Name | TaLender |
| --- | --- |
| Objective | Connect people who offer skills with people who seek them; enable discovery, preference/match, and real‑time chat. |
| Scope | Auth (email+Google), profile & skills, discovery with filters/sort, swipe-like preference & match, chat & messages, basic moderation, location opt‑in endpoints. |
| Users & Roles | End User; Moderator (remove content, delete abusive accounts). |
| Tech Stack | Frontend: React (Vite, TypeScript) • Backend: Node.js (Express, TypeScript) • DB: MongoDB (Mongoose) • Auth: JWT + Google OAuth • Realtime: Socket.IO |
| Timeframe | 2 months total — 4 Sprints × 2 weeks |
| Team | Wei • Luca • Simone |
| Deliverables | Running system; GitHub repo; input.txt, DataMetrics.json, Student_doc.md; estimation & process booklet. |

# 2. Scrum Plan

## Sprint 1 — Auth, Profile & Skills baseline

Stories

US-1 Create account

US-2 Login

US-3 Modify account data

US-4 Access main page

US-5 Modify offered skills

US-17 Logout

US-6 Delete account

## Sprint 2 — Discovery, Filters/Sorting, Swipe & Preference (2 weeks)

Stories

US-7 Select interested skills

US-10 Show relevant skills

US-11 Filter skills

US-12 Sort skills

US-13 Swipe one-by-one

US-19 Edit interests and filters

## Sprint 3 — Chat, Messaging & Match Notifications (2 weeks)

Stories

US-14 Instant chat with matches

US-20 Message other users

US-15 Receive match notification

## Sprint 4 — Moderation, Location Opt‑in, Hardening & Docs (2 weeks)

Stories

US-8 Report inappropriate content

US-9 Moderator removes inappropriate content

US-16 Moderator deletes accounts

US-18 Share location (opt-in)

# 3. Application Mockups

Mockups

# 4. Function Point Analysis

## 4.1 Inventory & Classification

| ILF | Complexity | Weight | FPs |
| --- | --- | --- | --- |
| Accounts | Average | 10 | 10 |
| Users | Average | 10 | 10 |
| Skills | Average | 10 | 10 |
| Categories | Low | 7 | 7 |
| Chats | Low | 7 | 7 |
| Messages | Average | 10 | 10 |
| Preferences | Low | 7 | 7 |

Subtotal ILF = 61

| EI | Complexity | Weight | FPs |
| --- | --- | --- | --- |
| POST /register | Average | 6 | 6 |
| POST /login | Low | 4 | 4 |
| POST api/logout | Low | 4 | 4 |
| POST /api/edit-user | Average | 6 | 6 |
| POST /api/delete-user | Average | 6 | 6 |
| POST /api/skills/add | Average | 6 | 6 |
| POST /api/user/preference | Average | 6 | 6 |
| POST /api/chats | Average | 6 | 6 |
| POST /api/messages/send | Average | 6 | 6 |

Subtotal EI = 50

| EO | Complexity | Weight | FPs |
| --- | --- | --- | --- |
| GET /api/recommendedUsers | Average | 7 | 7 |
| GET /api/categories | Low | 5 | 5 |
| GET /api/userId | Low | 5 | 5 |

Subtotal EO = 17

| EQ | Complexity | Weight | FPs |
| --- | --- | --- | --- |
| GET /api/skills (filter/sort) | Average | 4 | 4 |
| GET /api/users/search-by-username/:username | Low | 3 | 3 |
| GET /api/user/:id/skills | Low | 3 | 3 |
| GET /api/messages (paged) | Average | 4 | 4 |
| GET /api/chats/user | Average | 4 | 4 |

Subtotal EQ = 18

No EIF. UFP (Unadjusted Function Points) = 61 + 50 + 17 + 18 = 146

# 5. Sizing & COCOMO II

## 5.1 FP → LOC

| UFP | 146 |
| --- | --- |
| LOC/FP | 30 |
| SLOC (UFP × LOC/FP) | 4380 LOC (KLOC = 4.38) |

## 5.2 COCOMO II

E = B + 0.01 × ΣSF  →  E = 0.91 + 0.01 × 18.97 = 1.0997

PM = A × KLOC^E     →  PM = 2.94 × 4.38^1.0997 ≈ 14.92 PM

F = D + 0.2 × (E−B) →  F = 0.28 + 0.2 × (1.0997−0.91) = 0.31794

TDEV = C × PM^F     →  TDEV = 3.67 × 14.92^0.31794 ≈ 8.67 months

# 6. Project Analysis

## 6.1 Front-end Architecture

The following diagram illustrates the overall architecture of the frontend system.

It is organized into four main layers: Business, Data, Network, and Build. Each responsible for a specific aspect of the application, ensuring a modular, maintainable, and efficient frontend implementation.

## 6.2 ER Schema

The following ER diagram visually represents the relationships between the key entities in the system, such as users, profiles, skills and message. This diagram serves as a blueprint for the database schema, ensuring that all user stories and functionalities are supported efficiently.

7. System architecture

The Talender Application follows a layered client-server architecture, consisting of three main components:

• Frontend (React/Typescript/MUI/Vite): Provides the website interface for all users.

•⁠  ⁠Backend (Node.js/Express/Socket/Mongoose): Handles authentication, Rest requests, Real time chatting and connection to a remote Database

•⁠  ⁠Database (MongoDB): Stores user profiles, accounts, messages, chats and all the information present on the website.

The following diagram illustrates the high-level architecture of the system:

8. Conclusion

This document presented the Talender application, outlining its development through Agile Scrum methodology, Function Point and COCOMO II effort estimation, and a detailed architectural overview.

The application offers a dynamic and user-friendly platform that connects people based on their skills and interests, allowing them to discover potential matches and start a real-time chat.

The use of modern technologies and agile practices ensured iterative progress, fast feedback, and a clean, scalable codebase.